## 202002061809
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Cancelled | Low | Add for every file a description
49 | Done | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Cancelled | Low | Support User defined interrupts | Tag: SVC | Not needed because concept is to directly extend the interrupt service routine in the c file
59 | Open | Low | Support led user code | Tag: LED
60 | Cancelled | Low | MISRA Checker (additional) | there does not exist a free MISRA checker
61 | Open | Low | Data and Instruction trace to check the task activation order | See tools\ARM ETM mit openocd auslesen - Mikrocontroller.net.htm
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
65 | Open | Low | Fix every TODO in source code
66 | Done | Low | Add runtime resource monitoring | Added TODOs for this topic in source code
67 | Open | Low | Add Snooper functionality to setup
68 | Open | High | Add Kernel API for follow categories: 1. Process control a) create process (for example, fork on Unix-like systems, or NtCreateProcess in the Windows NT Native API) b) terminate process c) load, execute d) get/set process attributes e) wait for time, f) wait event/ signal event g) allocate and free memory | a) OS_CREATE_TASK b) OS_TERMINATE_TASK c) OS_START_TASK d) via task_s/task_t structure e) OS_SLEEP_TASK f)??? g) OS_CALLOC / OC_REALLOC / OS_MALLOC / OS_free
69 | Cancelled | High | 2. File management a) create file, delete file b) open, close c) read, write, reposition d) get/set file attributes | (no memory to store files exist in embedded systems, EEPROM is far to small) a) - b) - c) - d) -
70 | Open | High | 3. Device management a) request device, release device b) read, write, reposition c) get/set device attributes d) logically attach or detach devices | a) ??? b) ??? c) ??? d) ???
71 | Done | High | 4. Information maintenance a) get/set time or date b) get/set system data c) get/set process, file, or device attributes | a) - b) - (because info is determined at compile time) c) only allowed for system to read task info via task structure, files do not exist, devices use complex device drivers
72 | Open | High | 5. Communication a) create, delete communication connection b) send, receive messages c) transfer status information d) attach or detach remote devices | a) ??? b) ??? c) ??? d) ???
73 | Cancelled | High | 6. Protection a) get/set file permissions | a) ??? Files are not supported
74 | Open | Low | Enforce naming convention
75 | Open | Low | Enforce code style convention
76 | Open | Low | Implement EEP emulation
77 | Done | Low | Prevent ram variables (static) which are not mapped to a linker section to enforce MPU policy | Update: 5.2.20: all static variables marked with TODO -> closed
78 | Open | Low | Multicore support (OS_GET_CORE_ID, task system,…)
79 | Open | Low | Add support for other MCUs
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 202002051554
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Cancelled | Low | Add for every file a description
49 | Done | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
65 | Open | Low | Fix every TODO in source code
66 | Open | Low | Add runtime resource monitoring
67 | Open | Low | Add Snooper functionality to setup
68 | Open | High | Add Kernel API for follow categories: 1. Process control a) create process (for example, fork on Unix-like systems, or NtCreateProcess in the Windows NT Native API) b) terminate process c) load, execute d) get/set process attributes e) wait for time, f) wait event/ signal event g) allocate and free memory | a) OS_CREATE_TASK b) OS_TERMINATE_TASK c) OS_START_TASK d) via task_s/task_t structure e) OS_SLEEP_TASK f) - (operating system is time triggered only by design) g) OS_CALLOC / OC_REALLOC / OS_MALLOC / OS_free
69 | Open | High | 2. File management a) create file, delete file b) open, close c) read, write, reposition d) get/set file attributes | (no memory to store files exist in embedded systems, EEPROM is far to small) a) - b) - c) - d) -
70 | Open | High | 3. Device management a) request device, release device b) read, write, reposition c) get/set device attributes d) logically attach or detach devices | a) ??? b) ??? c) ??? d) ???
71 | Open | High | 4. Information maintenance a) get/set time or date b) get/set system data c) get/set process, file, or device attributes | a) ??? b) ??? c) ???
72 | Open | High | 5. Communication a) create, delete communication connection b) send, receive messages c) transfer status information d) attach or detach remote devices | a) ??? b) ??? c) ??? d) ???
73 | Open | High | 6. Protection a) get/set file permissions | a) ???
74 | Open | Low | Enforce naming convention
75 | Open | Low | Enforce code style convention
76 | Open | Low | Implement EEP emulation
77 | Done | Low | Prevent ram variables (static) which are not mapped to a linker section to enforce MPU policy | Update: 5.2.20: all static variables marked with TODO -> closed
78 | Open | Low | Multicore support (OS_GET_CORE_ID, task system,…)
79 | Open | Low | Add support for other MCUs
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20191002
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Cancelled | Low | Add for every file a description
49 | Done | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
65 | Open | Low | Fix every TODO in source code
66 | Open | Low | Add runtime resource monitoring
67 | Open | Low | Add Snooper functionality to setup
68 | Open | High | Add Kernel API for follow categories: 1. Process control a) create process (for example, fork on Unix-like systems, or NtCreateProcess in the Windows NT Native API) b) terminate process c) load, execute d) get/set process attributes e) wait for time, f) wait event/ signal event g) allocate and free memory | a) OS_CREATE_TASK b) OS_TERMINATE_TASK c) OS_START_TASK d) via task_s/task_t structure e) OS_SLEEP_TASK f) - (operating system is time triggered only by design) g) OS_CALLOC / OC_REALLOC / OS_MALLOC / OS_free
69 | Open | High | 2. File management a) create file, delete file b) open, close c) read, write, reposition d) get/set file attributes | (no memory to store files exist in embedded systems, EEPROM is far to small) a) - b) - c) - d) -
70 | Open | High | 3. Device management a) request device, release device b) read, write, reposition c) get/set device attributes d) logically attach or detach devices | a) ??? b) ??? c) ??? d) ???
71 | Open | High | 4. Information maintenance a) get/set time or date b) get/set system data c) get/set process, file, or device attributes | a) ??? b) ??? c) ???
72 | Open | High | 5. Communication a) create, delete communication connection b) send, receive messages c) transfer status information d) attach or detach remote devices | a) ??? b) ??? c) ??? d) ???
73 | Open | High | 6. Protection a) get/set file permissions | a) ???
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190927
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Cancelled | Low | Add for every file a description
49 | Done | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
65 | Open | Low | Fix every TODO in source code
66 | Open | Low | Add runtime resource monitoring
67 | Open | Low | Add Snooper functionality to setup
68 | Open | High | Add Kernel API for follow categories: 1. Process control a) create process (for example, fork on Unix-like systems, or NtCreateProcess in the Windows NT Native API) b) terminate process c) load, execute d) get/set process attributes e) wait for time, f) wait event/ signal event g) allocate and free memory | a) OS_CREATE_TASK b) OS_TERMINATE_TASK c) OS_START_TASK d) ????? e) ????? f) ???? g) OS_CALLOC / OC_REALLOC / OS_MALLOC / OS_free
|  |  | 2. File management a) create file, delete file b) open, close c) read, write, reposition d) get/set file attributes | a) ??? b) ??? c) ??? d) ???
|  |  | 3. Device management a) request device, release device b) read, write, reposition c) get/set device attributes d) logically attach or detach devices | a) ??? b) ??? c) ??? d) ???
|  |  | 4. Information maintenance a) get/set time or date b) get/set system data c) get/set process, file, or device attributes | a) ??? b) ??? c) ???
|  |  | 5. Communication a) create, delete communication connection b) send, receive messages c) transfer status information d) attach or detach remote devices | a) ??? b) ??? c) ??? d) ???
|  |  | 6. Protection a) get/set file permissions | a) ???
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190922
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Cancelled | Low | Add for every file a description
49 | Done | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
65 | Open | Low | Fix every TODO in source code
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190916
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Open | Low | Add for every file a description
49 | Open | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Done | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190915
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Open | Low | Add for every file a description
49 | Open | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Open | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190914
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Open | Low | Add for every file a description
49 | Open | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Done | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Open | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63 | Open | Low | ACL on task level, so every task has a set of rights, also implement system call which provide a mechanism for an task to access priviliged resources (system call uses ACL for check of rights) (from safety and security point of view) | Tag: ACL
64 | Open | High | Inter Task communication -> add os_intertask_com.c to bat files -> fill file with content to allow defined communication between tasks | Tag: IPC/ITC
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190908
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Done | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Open | Low | Add for every file a description
49 | Open | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Open | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Open | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63
64
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190906
Issue number | State | Prio | Topic | Details
1 | Done | High | Integrate STM32F4 example into Git repository | download net yet working
2 | Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
3 | Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
4 | Done | High | SW linking for x86 target
5 | Done | Low | SW linking for ARM target
6 | Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
7 | Done | Low | os_common
8 | Done | Low | os_exception.c
9 | Done | Low | os_exception_handler.c
10 | Done | Low | os_exception_table.c
11 | Done | High | os_init_task_system.c
12 | Done | High | os_main.c | see comments in the os_main.c
13 | Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
14 | Done | High | os_memory_virtualisation.c | 8 MPU regions exist
15 | Done | Low | os_ram.c
16 | Done | Low | os_shutdown.c
17 | Done | Low | os_stack.c
18 | Done | Low | os_start_ext_prg.c
19 | Done | Low | os_start_init_hw
20 | Done | High | os_start_init_mc
21 | Done | High | os_start_init_sw
22 | Done | High | os_start_os.c
23 | Done | High | os_task_common.c
24 | Done | High | os_task_queue.c
25 | Done | High | os_task_scheduler.c
26 | Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
27 | Cancelled | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
28 | Cancelled | Low | download.bat fehlerhaft
29 | Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
30 | Cancelled | Low | multicore changes (including task system)
31 | Done | Low | os_heap.c
32 | Done | High | lld_global.c
33 | Done | High | lld_interrupt.c
34 | Done | Low | lld_mmu.c | 8 MPU regions exist
35 | Done | High | lld_power.c
36 | Done | Low | lld_timer.s
37 | Done | Low | lld_watchdog.s
38 | Open | High | Komponententest
39 | Open | High | Traceability von Anforderungen zu Implementierung / Test
40 | Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
41 | Open | High | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
42 | Done | High | Stack cookie feature
43 | Done | High | Create component test infrastructure
44 | Open | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
45 | Done | Low | os_determine_next_task_activation
46 | Done | High | OS_TaskDispatcher handling
47 | Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
48 | Open | Low | Add for every file a description
49 | Open | Low | Add for every extern declaration / function definition a description
50 | Done | High | Fix every TODO in source code
51 | Done | Low | introduce naming convention for functions and variables (capital letter, ….)
52 | Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
53 | Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
54 | Done | High | Update to current cppcheck version 1.89
55 | Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
56 | Open | Low | Support multiply and devide of big integers | Tag: Big Int
57 | Open | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
58 | Open | Low | Support User defined interrupts | Tag: SVC
59 | Open | Low | Support led user code | Tag: LED
60 | Open | Low | MISRA Checker (additional)
61 | Open | Low | Data and Instruction trace to check the task activation order
62 | Open | Low | GUI für gdb suchen und zum laufen bringen
63
64
Note on D14: Autor: Basic MPU config used.
Note on D29: Autor: Flash is done via ST-Link
Note on D37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190905
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Open | Low | Add for every file a description
Open | Low | Add for every extern declaration / function definition a description
Open | Low | Fix every TODO in source code
Done | Low | introduce naming convention for functions and variables (capital letter, ….)
Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
Done | High | Update to current cppcheck version 1.89
Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190904
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Open | Low | Add for every file a description
Open | Low | Add for every extern declaration / function definition a description
Open | Low | Fix every TODO in source code
Open | Low | introduce naming convention for functions and variables (capital letter, ….)
Open | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
Open | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190709
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190706
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190703
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190624
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190621
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190619
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190618
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190612
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Open | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20190118
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20181230
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20181219
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20181017
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180917
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180916
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180811_0915_0916
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180803_04
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c

## 20180611
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Open | High | lld_power.c

## 20180122
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Done | High | os_memory_virtualisation.c | not possible in CortexM family
Done | High | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Open | High | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
Open | High | lld_mmu.c
Open | High | lld_power.c

## 20180120
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Done | High | os_memory_virtualisation.c | not possible in CortexM family
Done | High | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Open | Low | os_stack.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Open | High | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
Open | High | lld_mmu.c
Open | High | lld_power.c

## 20171011
State | Prio | Topic | Details
Open | Low | Integrate STM32F4 example into Git repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Open | Low | os_exception.c
Open | Low | os_exception_handler.c
Open | Low | os_exception_table.c
Done | High | os_init_task_system.c
Open | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | Low | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Open | Low | os_stack.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)

## 20160602
State | Prio | Topic | Details
Open | Low | Integrate STM32F4 example into Baazar repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Open | High | SW linking for x86 target
Open | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Open | Low | os_common
Open | Low | os_driver_hook
Open | Low | os_exception.c
Open | Low | os_exception_handler.c
Open | Low | os_exception_table.c
Done | High | os_init_task_system.c
Open | High | os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Open | Low | os_shutdown.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Open | Low | os_start_core.s
Open | Low | os_start_vector.s
Open | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)

## 20160601
State | Prio | Topic | Details
Open | High | Integrate STM32F4 example into Baazar repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done |  | SW linking for x86 and ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | Low | os_acl
Open | Low | os_common
Open | Low | os_driver_hook
Open | High | os_exception.c
Open | High | os_exception_handler.c
Open | High | os_exception_table.c
Open | High | os_init_task_system.c
Open | High | os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | Low | os_rte_common.c
Open | Low | os_rte_icc.c
Open | Low | os_shutdown.c
Open | Low | os_start_ext_prg.c
Open | High | os_start_init*
Open | High | os_start_os.c
Open | High | os_task_common.c
Open | High | os_task_queue.c
Open | High | os_task_scheduler.c
Open | High | os_start_core.s
Open | High | os_start_vector.s