## 20190906
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc) | Tag: PLL
Done | Low | os_determine_next_task_activation
Done | High | OS_TaskDispatcher handling
Done | Low | Overflow handling Time (solved via usage of 128 bit integer, update of global time is done every fixed cycle in function OS_EXCEPTION_SYSTICK() and every timer read)
Open | Low | Add for every file a description
Open | Low | Add for every extern declaration / function definition a description
Done | High | Fix every TODO in source code
Done | Low | introduce naming convention for functions and variables (capital letter, ….)
Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
Done | High | Update to current cppcheck version 1.89
Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
Open | Low | Support multiply and devide of big integers | Tag: Big Int
Open | Low | Support Process and Main stack MSP/PSP | Tag: MSP_PSP
Open | Low | Support User defined interrupts | Tag: SVC
Open | Low | Support led user code | Tag: LED
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190905
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Open | Low | Add for every file a description
Open | Low | Add for every extern declaration / function definition a description
Open | Low | Fix every TODO in source code
Done | Low | introduce naming convention for functions and variables (capital letter, ….)
Done | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
Done | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
Done | High | Update to current cppcheck version 1.89
Done | High | Move static variables to global (can be analyzed via readsize.bat) stack_pos stack_used TASK_0 TASK_1 TASK_2 TASK_3 call_nr
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190904
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Open | Low | Add for every file a description
Open | Low | Add for every extern declaration / function definition a description
Open | Low | Fix every TODO in source code
Open | Low | introduce naming convention for functions and variables (capital letter, ….)
Open | Low | Every RAM allocation shall be done in os_ram.c / os_ram_shared.c
Open | Low | Every number assignment to an unsigned variable shall be postfixed with "u"
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190709
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Open | Low | Configure PLL (see os_start_init_mc)
Open | Low | OS_DetermineNextTaskActivation, OS_TaskDispatcher handling
Open | Low | Overflow handling Time
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190706
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | High | Komponententest
Open | High | Traceability von Anforderungen zu Implementierung / Test
Open | High | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Done | High | Create component test infrastructure
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190703
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190624
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Done | High | Stack cookie feature
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190621
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Open | Low | Erweitere Sput um: a) Testname + RQ Id kann angegeben werden b) Report wird über erstellt (über welche RQs werden in welchen Tests geprüft) c) Ungetestete Anforderungen anzeigen d) Coverage anzeigen
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190619
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Open | Low | Anforderungsdokument schreiben (Anforderungen sollen die öffentlichen Schnittstellen auf C-Ebene entahlten, um direkt testbar zu sein)(welche c/h Dateien (inkl. Testdateien) gehören zu welcher Komponente,… Komponentenliste als Ergänzung der RQ schreiben)
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190618
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Done | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C14: Autor: Basic MPU config used.
Note on C29: Autor: Flash is done via ST-Link
Note on C37: Autor: der M4 hat nur einen DWT Timer, daher kein seperater Support hier nötig

## 20190612
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Done | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Open | Low | lld_timer.s
Done | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20190118
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c | 8 MPU regions exist
Done | High | os_memory_virtualisation.c | 8 MPU regions exist
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
- | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | 8 MPU regions exist
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20181230
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Cancelled | Low | download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test
Note on C29: Autor: Flash is done via ST-Link

## 20181219
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20181017
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Done | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Done | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
Done | Low | lld_mmu.c | see en.DM00046982.pdf page 192, not implemented in STM32F4 discovery board.
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180917
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4) https://www.mikrocontroller.net/topic/265600
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180916
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180811_0915_0916
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Done | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c
Open | Low | lld_timer.s
Open | Low | lld_watchdog.s
Open | Low | Komponententest
Open | Low | Traceability von Anforderungen zu Implementierung / Test

## 20180803_04
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
on_hold | Low | os_start_init_mc | os_start_init_mc is doing only peripheral now, the basic mcu init is done in os_exception_reset.s
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Done | High | lld_power.c

## 20180611
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | Low | os_common
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
on_hold | Low | os_memory_mmu_setup.c | see en.DM00046982.pdf page 192
Done | High | os_memory_virtualisation.c | see en.DM00046982.pdf page 192
Done | High | os_ram.c
on_hold | Low | os_rte_common.c
on_hold | Low | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | High | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
on_hold | Low | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
on_hold | Low | lld_mmu.c
Open | High | lld_power.c

## 20180122
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Done | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Done | High | os_memory_virtualisation.c | not possible in CortexM family
Done | High | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Done | Low | os_stack.c
Done | Low | os_start_ext_prg.c
Done | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Open | High | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
Open | High | lld_mmu.c
Open | High | lld_power.c

## 20180120
State | Prio | Topic | Details
Done | High | Integrate STM32F4 example into Git repository | download net yet working
Done | High | Make build files mostly indepent from exe-names (tools), program locations, etc
Done | High | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Done | Low | os_exception.c
Done | Low | os_exception_handler.c
Done | Low | os_exception_table.c
Done | High | os_init_task_system.c
Done | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Done | High | os_memory_virtualisation.c | not possible in CortexM family
Done | High | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Open | Low | os_stack.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)
Open | High | os_diagnostic_main.c
download.bat fehlerhaft
Done | High | bin File zum Download ist riesig, weil das RAM offset mit 0x40000000 vollkommen falsch ist 0x40000000 = ~ 1 GB
Open | Low | multicore changes (including task system)
Done | Low | os_heap.c
Open | High | lld_global.c
Done | High | lld_interrupt.c
Open | High | lld_mmu.c
Open | High | lld_power.c

## 20171011
State | Prio | Topic | Details
Open | Low | Integrate STM32F4 example into Git repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done | High | SW linking for x86 target
Done | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Done | Low | os_common
Open | Low | os_driver_hook
Open | Low | os_exception.c
Open | Low | os_exception_handler.c
Open | Low | os_exception_table.c
Done | High | os_init_task_system.c
Open | High | os_main.c | see comments in the os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | Low | os_ram.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Done | Low | os_shutdown.c
Open | Low | os_stack.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Done | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)

## 20160602
State | Prio | Topic | Details
Open | Low | Integrate STM32F4 example into Baazar repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Open | High | SW linking for x86 target
Open | Low | SW linking for ARM target
Open | Low | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | High | os_acl
Open | Low | os_common
Open | Low | os_driver_hook
Open | Low | os_exception.c
Open | Low | os_exception_handler.c
Open | Low | os_exception_table.c
Done | High | os_init_task_system.c
Open | High | os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | High | os_rte_common.c
Open | High | os_rte_icc.c
Open | Low | os_shutdown.c
Open | Low | os_start_ext_prg.c
Open | Low | os_start_init_hw
Open | Low | os_start_init_mc
Done | High | os_start_init_sw
Done | High | os_start_os.c
Done | High | os_task_common.c
Done | High | os_task_queue.c
Done | High | os_task_scheduler.c
Open | Low | os_start_core.s
Open | Low | os_start_vector.s
Open | High | List file with mixed C and assembler code needs to be generated and stored into *.lst
Open | High | Bootloader: Simpler loader expecting at fixed address with no download possibility (first step)

## 20160601
State | Prio | Topic | Details
Open | High | Integrate STM32F4 example into Baazar repository | download net yet working
Done |  | Make build files mostly indepent from exe-names (tools), program locations, etc
Open | Low | Implement heap option | heap shall be configured at task creation (mpu region, size, etc)
Done |  | SW linking for x86 and ARM target
Open | High | Debug for both targets not yet possible (e.g. gdb on x86 and Segger ICD for Cortex M4)
Open | Low | os_acl
Open | Low | os_common
Open | Low | os_driver_hook
Open | High | os_exception.c
Open | High | os_exception_handler.c
Open | High | os_exception_table.c
Open | High | os_init_task_system.c
Open | High | os_main.c
Open | Low | os_memory_mmu_setup.c
Open | Low | os_memory_virtualisation.c
Open | Low | os_rte_common.c
Open | Low | os_rte_icc.c
Open | Low | os_shutdown.c
Open | Low | os_start_ext_prg.c
Open | High | os_start_init*
Open | High | os_start_os.c
Open | High | os_task_common.c
Open | High | os_task_queue.c
Open | High | os_task_scheduler.c
Open | High | os_start_core.s
Open | High | os_start_vector.s